## Progress Features Q4
Team Name | Priority | Type | Feature | Epic owner | Scope | Initial status | Planned delivery sprint | Planned due date | Comments | Current completion | S1 | S2 | S3 | S4 | S5 | IP (forecast)
Blue | 1 | Story | Feature-074 | Persona 1 | Initial | New | S2 | 2025-10-28 |  | 100 | 95 | 95 | 100 | 100 | 100
Blue | 1 | Story | Feature-198 | Persona 1 | Initial | New | S4 | 2025-11-25 |  | 100 |  |  |  |  | 100
Blue | 1 | Story | Feature-199 | Persona 1 | Initial | New | S5 | 2025-12-09 |  | 100 |  |  |  |  | 100
Blue | 1 | Story | Feature-200 | Persona 1 | Initial | New | UNC | 2025-12-24 |  | 100 |  |  |  |  | 100
Blue | 1 | Story | Feature-136 | Persona 1 | Initial | New | UNC | 2025-12-24 |  | 100 |  |  |  |  | 100
Blue | 1 | Story | Feature-137 | Persona 1 | Initial | In Progress | UNC | 2025-12-24 |  | 100 | 0 |  |  | 100 | 100
Orange | 1 | Story | Feature-173 | Persona 1 | Initial | New | S5 | 2025-12-09 |  | 100 |  |  |  |  | 100
Orange | 1 | Story | Feature-174 | Persona 1 | Initial | New | S5 | 2025-12-09 |  | 100 | 0 | 0 | 0 | 0 | 100
Orange | 4 | Story | Feature-059 | Persona 2 | Initial | New | UNC | 2025-12-24 |  | 0
Orange | 4 | Story | Feature-058 | Persona 2 | Initial | In Progress | UNC | 2025-12-24 |  | 0
Blue | 5 | Story | Feature-171 | Persona 2 | Initial | New | UNC | 2025-12-24 |  | 100 | 10 | 10 | 10 | 20 | 100
Yellow | 6 | Feature | Feature-024 | Persona 3 | Initial | Ready | S3 | 2025-11-12 |  | 70 | 15 | 30 | 45 | 70
Yellow | 6 | Feature | Feature-025 | Persona 4 | Initial | New | S3 | 2025-11-12 |  | 70 | 15 | 30 | 45 | 70
Yellow | 6 | Feature | Feature-026 | Persona 5 | Initial | New | S4 | 2025-11-25 |  | 70 | 15 | 30 | 45 | 70
Green | 7 | Feature | Feature-036 | Persona 4 | Initial | In Progress | S4 | 2025-11-25 |  | 100 | 65 | 85 | 90 | 90 | 100
Turquoise | 7 | Feature | Feature-010 | Persona 4 | Initial | New | S1 | 2025-10-14 |  | 30 | 30
Turquoise | 7 | Feature | Feature-066 | Persona 4 | Initial | New | S1 | 2025-10-14 |  | 30 | 30
Lavender | 8 | Feature | Feature-037 | Persona 4 | Initial | In Progress | S1 | 2025-10-14 |  | 100 | 50 | 100 | 100 | 100 | 100
Lavender | 8 | Feature | Feature-038 | Persona 4 | Initial | New | S2 | 2025-10-28 |  | 100 | 50 | 100 | 100 | 100 | 100
Turquoise | 8 | Feature | Feature-039 | Persona 4 | Initial | New | S1 | 2025-10-14 |  | 100 | 0 | 0 | 0 | 0 | 100
Lavender | 9 | Feature | Feature-104 | Persona 5 | Initial | In Progress | S2 | 2025-10-28 |  | 100 | 65 |  |  | 70 | 100
Turquoise | 9 | Feature | Feature-105 | Persona 5 | Initial | In Progress | S3 | 2025-11-12 |  | 100 | 50 | 50 | 50 | 50 | 100
Lavender | 9 | Feature | Feature-194 | Persona 5 | Initial | New | S1 | 2025-10-14 |  | 100 | 55 | 70 | 75 | 80 | 100
Lavender | 9 | Feature | Feature-195 | Persona 5 | Initial | New | S2 | 2025-10-28 |  | 80 | 60 | 70 | 75 | 80
Turquoise | 9 | Feature | Feature-196 | Persona 5 | Initial | New | S1 | 2025-10-14 |  | 0 | 0 | 0 | 0 | 0
Green | 10 | Feature | Feature-142 | Persona 5 | Initial | New | S1 | 2025-10-14 | TTM | 100 | 80 | 100 | 100 | 100 | 100
Green | 10 | Feature | Feature-143 | Persona 5 | Initial | New | S3 | 2025-11-12 | TTM | 80 | 30 | 60 | 70 | 80
Turquoise | 10 | Feature | Feature-147 | Persona 5 | Initial | New | S4 | 2025-11-25 |  | 0 | 0 | 0 | 0 | 0
Lavender | 11 | Feature | Feature-123 | Persona 5 | Initial | Refine | S1 | 2025-10-14 |  | 75 | 65 | 70 | 75 | 75
Turquoise | 11 | Feature | Feature-124 | Persona 5 | Initial | New | S2 | 2025-10-28 |  | 30 | 30 | 30 | 30 | 30
Green | 12 | Feature | Feature-113 | Persona 5 | Initial | Refine | S1 | 2025-10-14 | Ready | 100 | 80 | 100 | 100 | 100 | 100
Green | 12 | Feature | Feature-114 | Persona 5 | Initial | New | S3 | 2025-11-12 |  | 80 | 40 | 60 | 80 | 80
Turquoise | 12 | Feature | Feature-115 | Persona 5 | Initial | New | S4 | 2025-11-25 |  | 30 | 30 | 30 | 30 | 30
Turquoise | 13 | Feature | Feature-069 | Persona 6 | Initial | New | S4 | 2025-11-25 |  | 0 | 0 | 0 | 0 | 0
Lavender | 13 | Feature | Feature-110 | Persona 6 | Initial | New | S2 | 2025-10-28 |  | 75 | 30 | 50 | 55 | 75
Lavender | 13 | Feature | Feature-111 | Persona 6 | Initial | New | S3 | 2025-11-12 |  | 0 | 0 | 0 | 0 | 0
Blue | 14 | Story | Feature-162 | Persona 7 | Initial | New | S1 | 2025-10-14 |  | 25 | 10 | 10 | 10 | 25
Orange | 14 | Story | Feature-164 | Persona 7 | Initial | New | UNC | 2025-12-24 |  | 0
Green | 14 | Feature | Feature-163 | Persona 8 | Initial | New | IP | 2025-12-24 |  | 30 | 0 | 10 | 20 | 30
Green | 15 | Feature | Feature-093 | Persona 6 | Initial | In Progress | S3 | 2025-11-12 |  | 100 | 60 | 80 | 95 | 95 | 100
Green | 15 | Feature | Feature-175 | Persona 6 | Initial | New | S3 | 2025-11-12 |  | 90 | 25 | 60 | 80 | 90
Green | 16 | Feature | Feature-057 | Persona 8 | Initial | In Progress | IP | 2025-12-24 |  | 50 | 20 | 30 | 40 | 50
Turquoise | 16 | Feature | Feature-125 | Persona 8 | Initial | Refine | S6 | 2025-12-24 |  | 0 | 0 | 0 | 0 | 0
Amber | 17 | Feature | Feature-117 | Persona 9 | Initial | New | S5 | 2025-12-09 |  | 33 | 16 | 16 | 16 | 33
Amber | 17 | Feature | Feature-151 | Persona 9 | Initial | New | S5 | 2025-12-09 |  | 30 | 0 | 0 | 7 | 30
Amber | 18 | Feature | Feature-020 | Persona 4 | Initial | New | UNC | 2025-12-24 |  | 41 | 25 | 25 | 33 | 41
Amber | 18 | Feature | Feature-035 | Persona 4 | Initial | New | S4 | 2025-11-25 |  | 60 | 44 | 55 | 60 | 60
Amber | 18 | Feature | Feature-140 | Persona 4 | Initial | New | S5 | 2025-12-09 |  | 78 | 52 | 64 | 78 | 73
Blue | 19 | Story | Feature-080 | Persona 6 | Initial | Ready for QA | S6 | 2025-12-24 |  | 90 |  |  | 90 | 90
Green | 19 | Feature | Feature-102 | Persona 6 | Initial | In Progress | S3 | 2025-11-12 |  | 100 | 45 | 60 | 95 | 95 | 100
Lavender | 19 | Feature | Feature-107 | Persona 6 | Initial | New | S2 | 2025-10-28 |  | 0 | 0 | 0 | 0 | 0
Turquoise | 19 | Feature | Feature-108 | Persona 6 | Initial | New | S6 | 2025-12-24 |  | 0
Lavender | 19 | Feature | Feature-129 | Persona 6 | Initial | Ready | S4 | 2025-11-25 |  | 75 | 20 | 50 | 65 | 75
Turquoise | 19 | Feature | Feature-131 | Persona 6 | Initial | In Progress | S6 | 2025-12-24 |  | 47 | 30 | 40 | 45 | 47
Amber | 19 | Feature | Feature-160 | Persona 6 | Initial | New | S5 | 2025-12-09 |  | 75 | 0 | 0 | 12 | 75
Green | 20 | Feature | Feature-005 | Persona 4 | Initial | In Progress | UNC | 2025-12-24 |  | 0 | 0 | 0 | 0 | 0
Green | 20 | Feature | Feature-006 | Persona 4 | Initial | In Progress | UNC | 2025-12-24 |  | 10 | 0 | 0 | 0 | 10
Turquoise | 21 | Feature | Feature-083 | Persona 3 | Initial | New | S5 | 2025-12-09 |  | 0
Amber | 21 | Feature | Feature-138 | Persona 3 | Initial | New | S5 | 2025-12-09 |  | 33 | 33 | 33 | 33 | 33
Turquoise | 22 | Feature | Feature-100 | Persona 3 | Initial | New | S5 | 2025-12-09 |  | 0
Amber | 22 | Feature | Feature-139 | Persona 3 | Initial | New | S6 | 2025-12-24 |  | 62 | 14 | 37 | 37 | 62
Green | 26 | Feature | Feature-019 | Persona 4 | Initial | New | IP | 2025-12-24 |  | 0 | 0 | 0 | 0 | 0
Green | 28 | Feature | Feature-047 | Persona 6 | Initial | Ready | S3 | 2025-11-12 |  | 40 | 0 | 0 | 20 | 40
Green | 28 | Feature | Feature-048 | Persona 6 | Initial | New | IP | 2025-12-24 |  | 0 | 0 | 0 | 0 | 0
Green | 29 | Feature | Feature-165 | Persona 6 | Initial | New | S4 | 2025-11-25 |  | 100 | 80 | 0 | 0 | 60 | 100
Green | 29 | Feature | Feature-166 | Persona 6 | Initial | New | IP | 2025-12-24 |  | 20 | 20 | 0 | 0 | 20
Orange | 30 | Story | Feature-068 | Persona 5 | Initial | In Progress | S6 | 2025-12-24 |  | 50 | 50 | 50 | 50 | 50
Green | 31 | Feature | Feature-084 | Persona 4 | Initial | New | S1 | 2025-10-14 |  | 100 | 60 | 70 | 80 | 80 | 100
Green | 31 | Feature | Feature-085 | Persona 4 | Initial | New | S5 | 2025-12-09 |  | 40 | 0 | 10 | 30 | 40
Green | 31 | Feature | Feature-086 | Persona 4 | Initial | New | S2 | 2025-10-28 |  | 60 | 0 | 20 | 45 | 60
Green | 31 | Feature | Feature-087 | Persona 4 | Initial | New | IP | 2025-12-24 |  | 10 | 0 | 0 | 0 | 10
Green | 31 | Feature | Feature-090 | Persona 4 | Initial | New | IP | 2025-12-24 |  | 0 | 0 | 0 | 0 | 0
Orange | 33 | Story | Feature-045 | Persona 10 | Initial | New | S2 | 2025-10-28 |  | 95 | 50 | 50 | 85 | 95
Orange | 33 | Story | Feature-046 | Persona 10 | Initial | New | S2 | 2025-10-28 |  | 95 | 50 | 50 | 85 | 95
Orange | 33 | Story | Feature-063 | Persona 10 | Initial | New | S5 | 2025-12-09 |  | 95 |  |  | 85 | 95
Orange | 33 | Story | Feature-064 | Persona 10 | Initial | New | S5 | 2025-12-09 |  | 95 |  |  | 85 | 95
Orange | 33 | Story | Feature-065 | Persona 10 | Initial | New | S5 | 2025-12-09 |  | 80 |  |  |  | 80
Orange | 33 | Story | Feature-062 | Persona 10 | Initial | New | S6 | 2025-12-24 |  | 0
Orange | 33 | Story | Feature-153 | Persona 10 | Initial | New | S6 | 2025-12-24 |  | 0
Orange | 33 | Story | Feature-191 | Persona 10 | Initial | New | S6 | 2025-12-24 |  | 0
Green | 36 | Feature | Feature-091 | Persona 5 | Initial | Refine | S2 | 2025-10-28 |  | 100 | 0 | 80 | 80 | 80 | 100
Green | 36 | Feature | Feature-049 | Persona 5 | Initial | New | S4 | 2025-11-25 |  | 60 | 0 | 20 | 40 | 60
Turquoise | 36 | Feature | Feature-130 | Persona 5 | Initial | New | S6 | 2025-12-24 |  | 0 | 0 | 0 | 0 | 0
Blue | 37 | Story | Feature-001 | Persona 11 | Initial | In Progress | UNC | 2025-12-24 | documented as is | 30 | 0 |  | 50 | 70
Orange | 38 | Story | Feature-154 | Persona 11 | Initial | New | UNC | 2025-12-24 |  | 100 |  |  |  | 100 | 100
Orange | 38 | Story | Feature-155 | Persona 11 | Initial | New | UNC | 2025-12-24 |  | 50 |  |  | 25 | 50
Orange | 39 | Story | Feature-095 | Persona 6 | Initial | In Progress | S6 | 2025-12-24 |  | 50 |  |  |  | 50
Blue | 41 | Story | Feature-099 | Persona 3 | Initial | New | UNC | 2025-12-24 |  | 20 | 0 | 0 | 20 | 20
Orange | 41 | Story | Feature-092 | Persona 3 | Removed | New | UNC | 2025-12-24 | Backlog | 0
Green | 42 | Feature | Feature-121 | Persona 3 | Initial | New | S2 | 2025-10-28 |  | 95 | 0 | 80 | 95 | 95
Green | 42 | Feature | Feature-122 | Persona 3 | Initial | New | IP | 2025-12-24 |  | 20 | 0 | 0 | 0 | 20
Amber | 42 | Feature | Feature-193 | Persona 3 | Initial | New | S6 | 2025-12-24 |  | 57 | 0 | 14 | 14 | 57
Green | 43 | Feature | Feature-002 | As per team name in colmun A | Initial | New | UNC | 2025-12-24 |  | 0 | 0 | 0 | 0 | 0
Blue | 44 | Story | Feature-004 | As per team name in colmun A | Initial | In Progress | UNC | 2025-12-24 |  | 100 | 15 | 15 | 15 | 15 | 100
Orange | 45 | Story | Feature-044 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 0
Yellow | 47 | Feature | Feature-070 | As per team name in colmun A | Initial | New | S3 | 2025-11-12 |  | 50 | 20 | 25 | 30 | 50
Turquoise | 47 | Feature | Feature-071 | As per team name in colmun A | Initial | New | S4 | 2025-11-25 |  | 80 | 80 | 80 | 80 | 80
Green | 48 | Feature | Feature-008 | As per team name in colmun A | Initial | In Progress | IP | 2025-12-24 |  | 0 | 0 | 0 | 0 | 0
Orange | 49 | Story | Feature-097 | As per team name in colmun A | Initial | New | UNC | 2025-12-24 |  | 100 |  |  |  |  | 100
Green | 51 | Feature | Feature-156 | As per team name in colmun A | Initial | New | S2 | 2025-10-28 | nothing to do | 100 | 0 | 100 | 100 | 100 | 100
Green | 51 | Feature | Feature-157 | As per team name in colmun A | Initial | New | IP | 2025-12-24 | nothing to do | 100 | 0 | 100 | 100 | 100 | 100
Yellow | 53 | Feature | Feature-012 | As per team name in colmun A | Initial | Refine | S4 | 2025-11-25 |  | 100 | 5 | 15 | 30 | 100
Green | 54 | Feature | Feature-149 | As per team name in colmun A | Initial | In Progress | S1 | 2025-10-14 |  | 100 | 80 | 100 | 100 | 100 | 100
Green | 54 | Feature | Feature-150 | As per team name in colmun A | Initial | Refine | S4 | 2025-11-25 | New | 100 | 40 | 100 | 100 | 100 | 100
Emerald | 56 | Feature | Feature-077 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 100 | 20 |  |  |  | 100
Emerald | 56 | Feature | Feature-051 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 0 | 0
Emerald | 56 | Feature | Feature-096 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 0 | 0
Emerald | 56 | Feature | Feature-148 | As per team name in colmun A | Initial | New | S4 | 2025-11-25 |  | 0 | 0
Emerald | 57 | Feature | Feature-052 | As per team name in colmun A | Initial | New | UNC | 2025-12-24 |  | 0 | 0
Emerald | 58 | Feature | Feature-081 | As per team name in colmun A | Initial | In Progress | UNC | 2025-12-24 |  | 50 | 50
Emerald | 59 | Feature | Feature-023 | As per team name in colmun A | Initial | New | S1 | 2025-10-14 |  | 0 | 0
Emerald | 60 | Feature | Feature-014 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 0 | 0
Azure | 62 | Feature | Feature-170 | As per team name in colmun A | Initial | New | S3 | 2025-11-12 |  | 80 | 20 | 40 | 60 | 80
Azure | 63 | Feature | Feature-144 | As per team name in colmun A | Initial | New | IP | 2025-12-24 |  | 40 | 5 | 10 | 20 | 40
Azure | 63 | Feature | Feature-145 | As per team name in colmun A | Initial | New | IP | 2025-12-24 |  | 20 | 5 | 10 | 20 | 20
Blue | 63 | Story | Feature-167 | As per team name in colmun A | Initial | New | S5 | 2025-12-09 |  | 70 | 25 | 25 | 25 | 90 | 100
Green | 63 | Feature | Feature-168 | As per team name in colmun A | Initial | New | S1 | 2025-10-14 |  | 100 | 60 | 60 | 80 | 90 | 100
Green | 63 | Feature | Feature-169 | As per team name in colmun A | Initial | New | IP | 2025-12-24 |  | 30 | 0 | 0 | 20 | 30
Yellow | 64 | Feature | Feature-082 | As per team name in colmun A | Initial | New | S5 | 2025-12-09 |  | 30 | 10 | 20 | 25 | 30
Emerald | 65 | Feature | Feature-158 | As per team name in colmun A | Initial | New | UNC | 2025-12-24 |  | 0 | 0
Emerald | 66 | Feature | Feature-159 | As per team name in colmun A | Initial | New | UNC | 2025-12-24 |  | 0 | 0
Green | 68 | Feature | Feature-161 | As per team name in colmun A | Initial | New | UNC | 2025-12-24 |  | 0 | 0 | 0 | 0 | 0
Amber | 69 | Feature | Feature-152 | As per team name in colmun A | Initial | New | UNC | 2025-12-24 |  | 30 | 0 | 25 | 25 | 30
Yellow | 69 | Feature | Feature-176 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 70 | 20 | 40 | 60 | 70
Yellow | 69 | Feature | Feature-177 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 70 | 20 | 40 | 60 | 70
Green | 69 | Feature | Feature-178 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 27 | 0 | 27 | 18 | 25
Yellow | 69 | Feature | Feature-179 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 70 | 20 | 40 | 60 | 70
Yellow | 69 | Feature | Feature-181 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 70 | 20 | 40 | 60 | 70
Yellow | 69 | Feature | Feature-182 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 70 | 20 | 40 | 60 | 70
Amber | 69 | Feature | Feature-183 | As per team name in colmun A | Initial | New | UNC | 2025-12-24 |  | 64 | 23 | 52 | 51 | 64
Azure | 69 | Feature | Feature-184 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 80 | 20 | 40 | 60 | 80
Azure | 69 | Feature | Feature-185 | As per team name in colmun A | Initial | New | IP | 2025-12-24 |  | 80 | 20 | 40 | 60 | 80
Yellow | 69 | Feature | Feature-186 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 70 | 20 | 40 | 60 | 70
Yellow | 69 | Feature | Feature-187 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 70 | 20 | 40 | 60 | 70
Yellow | 69 | Feature | Feature-188 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 70 | 20 | 40 | 60 | 70
Yellow | 69 | Feature | Feature-189 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 70 | 20 | 40 | 60 | 70
Azure | 69 | Feature | Feature-201 | As per team name in colmun A | Initial | New | UNC | 2025-12-24 |  | 80 | 20 | 40 | 60 | 80
Azure | 69 | Feature | Feature-126 | As per team name in colmun A | Initial | New | UNC | 2025-12-24 |  | 80 | 20 | 40 | 60 | 80
Yellow | 69 | Feature | Feature-207 | As per team name in colmun A | Initial | New | S4 | 2025-11-25 |  | 40 | 15 | 30 | 35 | 40
Yellow | 69 | Feature | Feature-208 | As per team name in colmun A | Initial | New | S2 | 2025-10-28 |  | 15 | 0 | 0 | 5 | 15
Emerald | 71 | Feature | Feature-141 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 0 | 0
Blue | 72 | Story | Feature-103 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 80 | 25 | 25 | 25 | 80
Blue | 72 | Story | Feature-197 | As per team name in colmun A | Initial | New | S6 | 2025-12-24 |  | 100 | 25 | 25 | 25 | 25 | 100
Green | 72 | Feature | Feature-209 | As per team name in colmun A | Added |  |  |  | Duplicate | 100 |  |  |  |  | 100
Green | 72 | Feature | Feature-094 | As per team name in colmun A | Debt |  |  |  |  | 100 | 60 | 100 | 100 | 100 | 100
Green | 72 | Feature | Feature-089 | As per team name in colmun A | Debt |  |  |  |  | 100 | 68 | 75 | 100 | 100 | 100
Green | 72 | Feature | Feature-088 | As per team name in colmun A | Debt |  |  |  |  | 100 | 71 | 68 | 100 | 100 | 100
Azure | 72 | Feature | Feature-016 | As per team name in colmun A | Debt |  |  |  |  | 100 | 20 | 40 | 60 | 60 | 100
Azure | 72 | Feature | Feature-015 | As per team name in colmun A | Added |  |  |  |  | 20 | 5 | 10 | 20 | 20
Amber | 72 | Feature | Feature-028 | As per team name in colmun A | Added |  |  |  |  | 0 | 0 | 0 | 0 | 0
Amber | 72 | Feature | Feature-202 | As per team name in colmun A | Debt |  |  |  |  | 78 | 25 | 70 | 57 | 78
Amber | 72 | Feature | Feature-128 | As per team name in colmun A | Debt |  |  |  |  | 50 | 37 | 50 | 50 | 50
Amber | 72 | Feature | Feature-116 | As per team name in colmun A | Debt |  |  |  |  | 80 | 50 | 60 | 80 | 72
Amber | 72 | Feature | Feature-101 | As per team name in colmun A | Debt |  |  |  |  | 94 | 88 | 94 | 94 | 94
Amber | 72 | Feature | Feature-056 | As per team name in colmun A | Added |  |  |  |  | 42 | 14 | 14 | 14 | 42
Amber | 72 | Feature | Feature-227 | As per team name in colmun A | Debt |  |  |  |  | 77 | 70 | 72 | 77 | 77
Orange | 72 | Feature | Feature-206 | As per team name in colmun A | Added |  |  |  |  | 75 | 25 | 25 | 50 | 75
Orange | 72 | Feature | Feature-146 | As per team name in colmun A | Added |  |  |  |  | 100 | 75 | 100 | 100 | 100 | 100
Orange | 72 | Feature | Feature-109 | As per team name in colmun A | Debt |  |  |  |  | 50 | 50 | 50 | 50 | 50
Orange | 72 | Feature | Feature-067 | As per team name in colmun A | Debt |  |  |  |  | 100 | 75 | 100 | 100 | 100 | 100
Orange | 72 | Feature | Feature-021 | As per team name in colmun A | Debt |  |  |  |  | 100 | 75 | 100 | 100 | 100 | 100
Orange | 72 | Feature | Feature-017 | As per team name in colmun A | Added |  |  |  |  | 50 | 25 | 25 | 50 | 50
Orange | 72 | Feature | Feature-007 | As per team name in colmun A | Added |  |  |  |  | 100 | 75 | 100 | 100 | 100 | 100
Orange | 72 | Feature | Feature-112 | As per team name in colmun A | Added |  |  |  |  | 100 | 25 | 25 | 50 | 50 | 100
Orange | 72 | Feature | Feature-027 | As per team name in colmun A | Added |  |  |  |  | 100 | 25 | 25 | 75 | 75 | 100
Blue | 72 | Story | Feature-211 | As per team name in colmun A | Added |  |  |  |  | 60 | 20 | 20 | 20 | 60
Blue | 72 | Story | Feature-210 | As per team name in colmun A | Added |  |  |  |  | 100 | 20 | 20 | 60 | 80 | 100
Blue | 72 | Story | Feature-135 | As per team name in colmun A | Debt |  |  |  |  | 100 | 25 | 25 | 25 | 100 | 100
Blue | 74 | Story | Feature-078 | As per team name in colmun A | Added |  |  |  |  | 25 | 10 | 10 | 10 | 25
Blue | 74 | Story | Feature-075 | As per team name in colmun A | Debt |  |  |  |  | 100 |  |  | 50 | 50 | 100
Blue | 74 | Story | Feature-073 | As per team name in colmun A | Debt |  |  |  |  | 100 |  |  | 100 | 100 | 100
Blue | 74 | Story | Feature-072 | As per team name in colmun A | Added |  |  |  |  | 100 |  |  | 100 | 100 | 100
Blue | 74 | Story | Feature-043 | As per team name in colmun A | Idea |  |  |  |  | 100 |  |  |  |  | 100
Blue | 74 | Story | Feature-042 | As per team name in colmun A | Added |  |  |  |  | 100 |  |  |  |  | 100
Blue | 74 | Story | Feature-034 | As per team name in colmun A | Added |  |  |  |  | 100 | 0 | 0 | 15 | 5 | 100
Blue | 74 | Story | Feature-033 | As per team name in colmun A | Idea |  |  |  |  | 0
Blue | 74 | Story | Feature-032 | As per team name in colmun A | Idea |  |  |  |  | 100 |  |  |  |  | 100
Blue | 74 | Story | Feature-011 | As per team name in colmun A | Idea |  |  |  | In evaluation | 10 |  |  | 20 | 25
Blue | 74 | Story | Feature-120 | As per team name in colmun A | Added |  |  |  |  | 100 | 100 | 100 | 100 | 100 | 100
Blue | 74 | Story | Feature-098 | As per team name in colmun A | Debt |  |  |  |  | 100 | 100 | 100 | 100 | 100 | 100
Blue | 74 | Story | Feature-050 | As per team name in colmun A | Added |  |  |  |  | 100 | 100 | 100 | 100 | 100 | 100
Blue | 74 | Story | Feature-040 | As per team name in colmun A | Added |  |  |  |  | 100 | 100 | 100 | 100 | 100 | 100
Blue | 74 | Story | Feature-009 | As per team name in colmun A | Added |  |  |  |  | 100 | 100 | 100 | 100 | 100 | 100
Blue | 74 | Story | Feature-217 | As per team name in colmun A | Debt |  |  |  |  | 50 |  |  |  |  | 100
Blue | 74 | Story | Feature-079 | As per team name in colmun A | Debt |  |  |  |  | 25 | 10 | 10 | 10 | 25
Yellow | 74 | Feature | Feature-018 | As per team name in colmun A | Added |  |  |  |  | 0
Orange | 74 | Story | Feature-215 | As per team name in colmun A | Added |  |  |  |  | 50 |  |  | 50 | 50
Orange | 77 | Story | Feature-134 | As per team name in colmun A | Added |  |  |  | Blocked | 25 | 25 | 25 | 25 | 25
Orange | 77 | Story | Feature-133 | As per team name in colmun A | Debt |  |  |  |  | 100 | 100 | 100 | 100 | 100 | 100
Orange | 77 | Story | Feature-060 | As per team name in colmun A | Debt |  |  |  |  | 25 | 25 | 25 | 25 | 25
Orange | 77 | Story | Feature-030 | As per team name in colmun A | Added |  |  |  |  | 0
Azure | 77 | Feature | Feature-214 | As per team name in colmun A | Added |  |  |  |  | 40 | 0 | 20 | 40 | 40
Silver | 77 | Feature | Feature-190 | As per team name in colmun A | Added |  |  |  |  | 0
Gold | 77 | Feature | Feature-180 | As per team name in colmun A | Added |  |  |  |  | 0
Yellow | 77 | Feature | Feature-055 | As per team name in colmun A | Debt |  |  |  |  | 0
Yellow | 77 | Feature | Feature-003 | As per team name in colmun A | Debt |  |  |  |  | 20 | 0 | 5 | 10 | 20
Yellow | 77 | Feature | Feature-127 | As per team name in colmun A | Added |  |  |  |  | 0
Azure | 77 | Feature | Feature-220 | As per team name in colmun A | Added |  |  |  |  | 100 | 0 | 0 | 20 | 20 | 100
Orange | 77 | Story | Feature-219 | As per team name in colmun A | Added |  |  |  |  | 100 | 0 | 0 | 75 | 100 | 100
Green | 77 | Feature | Feature-212 | As per team name in colmun A | Added |  |  |  |  | 50 |  |  | 35 | 50
Orange | 77 | Story | Feature-204 | As per team name in colmun A | Added |  |  |  |  | 100 | 0 | 0 | 0 | 100 | 100
Orange | 77 | Story | Feature-203 | As per team name in colmun A | Added |  |  |  |  | 100 |  |  | 25 | 100 | 100
Amber | 77 | Feature | Feature-119 | As per team name in colmun A | Added |  |  |  |  | 0 |  |  |  | 0
Orange | 80 | Story | Feature-053 | As per team name in colmun A | Debt |  |  |  |  | 25 | 0 | 0 | 25 | 25
Orange | 80 | Story | Feature-041 | As per team name in colmun A | Added |  |  |  |  | 0
Orange | 80 | Story | Feature-029 | As per team name in colmun A | Idea |  |  |  |  | 100 |  |  | 25 | 100 | 100
Amber | 80 | Feature | Feature-022 | As per team name in colmun A | Added |  |  |  |  | 33 |  |  |  | 33
Green | 80 | Feature | Feature-213 | As per team name in colmun A | Added |  |  |  |  | 0 |  |  | 0 | 0
Blue | 80 | Story | Feature-222 | As per team name in colmun A | Added |  |  |  |  | 0
Blue | 80 | Story | Feature-221 | As per team name in colmun A | Added |  |  |  |  | 0
Orange | 80 | Story | Feature-205 | As per team name in colmun A | Added |  |  |  |  | 25 | 0 | 0 | 0 | 25
Amber | 80 | Feature | Feature-192 | As per team name in colmun A | Added |  |  |  |  | 0 |  |  |  | 0
Green | 80 | Feature | Feature-132 | As per team name in colmun A | Added |  |  |  |  | 0
Maroon | 80 | Feature | Feature-106 | As per team name in colmun A | Added |  |  |  |  | 0
Blue | 80 | Story | Feature-076 | As per team name in colmun A | Added |  |  |  |  | 25 | 0 | 0 | 0 | 25
Orange | 80 | Story | Feature-031 | As per team name in colmun A | Idea |  |  |  |  | 75 |  |  |  | 75
Blue | 80 | Story | Feature-226 | As per team name in colmun A | Added |  |  |  |  | 0
Blue | 84 | Story | Feature-225 | As per team name in colmun A | Added |  |  |  |  | 0
Blue | 84 | Story | Feature-224 | As per team name in colmun A | Added |  |  |  |  | 0
Blue | 84 | Story | Feature-223 | As per team name in colmun A | Added |  |  |  |  | 0
Orange | 84 | Story | Feature-218 | As per team name in colmun A | Idea |  |  |  |  | 0
Blue | 84 | Story | Feature-216 | As per team name in colmun A | Added |  |  |  |  | 0
Yellow | 84 | Feature | Feature-172 | As per team name in colmun A | Added |  |  |  |  | 0
Amber | 84 | Feature | Feature-118 | As per team name in colmun A | Added |  |  |  |  | 0
Orange | 84 | Story | Feature-061 | As per team name in colmun A | Added |  |  |  |  | 0
Lavender | 84 | Feature | Feature-054 | As per team name in colmun A | Added |  |  |  |  | 100 |  |  |  | 100 | 100
Emerald | 84 | Feature | Feature-013 | As per team name in colmun A | Added |  |  |  |  | 0

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter | Select User... | Select User... | Select User...
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_dd/MM/yyyy HH:mm | readOnlyTestRange_General | Johan Van Hemelryk | Johan Van Hemelryk | Johan Van Hemelryk
|  |  |  | Kevin De Wolf | Kevin De Wolf | Kevin De Wolf
[5 empty] | Michiel Adams | Michiel Adams